## Slide 1
MarComms Operating Model Redesign
Executive Background & Project Plan

## Slide 2
Background: What We Have Learned
From Discovery Conversations
• MarComms operates in a complex, high-volume, matrixed environment
• Most work requires multiple teams and handoffs
• Review cycles are heavy and timelines remain long
• Ownership and visibility are not always clear
• Speed and integration are recurring challenges
• Teams are highly committed to quality and reputation
From Past Improvement Efforts
• This problem has been addressed multiple times before
• Some timelines improved initially
• Improvements were not sustained over time
• Many outputs remain slower than external benchmarks
• Deeper, systemic change has been hard to achieve
KEY INSIGHT
We have made progress before, but it has not scaled or lasted.
Based on discovery sessions with key stakeholders and functional leaders

## Slide 3
Why This Has Been Hard to Fix
Process & Structure
• Existing workflows are difficult to disrupt
• End-to-end ownership is unclear
• Different content types treated similarly
• Processes reflect history more than current needs
Culture & Behavior
• Strong emphasis on perfection over speed
• Risk aversion driven by past experiences
• "More work" sometimes seen as "more value"
• Many handoffs treated as individual jobs
Change & Adoption
• Past efforts focused on process, not behavior
• Change management was limited
• Stakeholder experience not always central
• Alignment on urgency has varied
External Pressure
• Faster-moving competitors
• New digital and AI channels emerging
• Changing content consumption patterns
• Rising expectations for responsiveness
KEY INSIGHT
This is not just a workflow problem. It is a system-level challenge spanning structure, culture, and adoption.
Sustainable improvement requires coordinated redesign across all four dimensions.

## Slide 4
Project Plan: MarComms Operating Model Redesign
This work starts with understanding why prior attempts stalled — not with process mapping
Phase 1
Deepen Problem Understanding
Weeks 1–4
• Discovery sessions with key stakeholders
• Review past improvement efforts
• Identify true bottlenecks vs. symptoms
• Segment work types by risk and complexity
Phase 2
Prioritize What to Reimagine
Weeks 5–6
• Identify priority areas by impact
• Decide what to redesign now vs. later
• Align on design principles
• Define what "good enough" means
Phase 3
Reimagine Operating Model
Weeks 7–11
• Redesign priority workflows end-to-end
• Clarify ownership and decision rights
• Build differentiation into the system
• Simplify handoffs and approvals
Phase 4
Change & Adoption
Weeks 5–12
• Stakeholder engagement throughout
• Leadership alignment on behaviors
• Communication and enablement plan
• Define success measures
GUIDING PRINCIPLES
Redesign before optimize
Focus on impact, not volume
Differentiate by risk
Build for adoption

## Slide 5
Timeline at a Glance
Week 1 2 3 4 5 6 7 8 9 10 11 12
Phase 1
Deep Problem Discovery
Phase 2
Prioritization & Focus
Phase 3
Operating Model Redesign
Phase 4
Change Management & Adoption
Phase
Focus
Timing
Key Outputs
1
Deep problem discovery
Weeks 1–4
Root cause analysis, evidence-based problem statement
2
Prioritization & focus
Weeks 5–6
Prioritized scope, executive alignment
3
Operating model redesign
Weeks 7–11
Future-state model, simplified workflows
4
Change & adoption
Weeks 5–12
Change strategy, adoption roadmap, success measures